## Sheet1
Project schedule (Updated) |  |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Organization
Seting up project environment & getting familiar with Unity | bar: 1 to 3
Requirements engineering | bar: 1
Planning & Scheduling | bar: 2
Project Initiation Document - PID | bar: 2
Base Product
Data acqusition & pre-processing | bar: 3
Building 3D scene in Unity | bar: 3 to 5
Developing user interface | bar: 4 to 6
2D layer integration | bar: 3 to 5
Additional Features
Uploading 3D models / 3D Urban master-plans | bar: 6 to 8
Synchronization with Open Data Portal | bar: 7 to 8
Temporal slider | bar: 6 to 8
Project Finalization
Final testing | bar: 9 to 10
Technical presentation - Nov. 5, 9:00 | bar: 9 to 10
Geomatics Day presentation - Nov. 8, 13:00 | bar: 10
Final report | bar: 4; 9 to 11
| Deadlines |  |  | 2: PID - Sep. 13, 17:00; 4: Midterm Report Sep. 26, 17:00; 5: Midterm Presentation Sep. 30, 9:00; 9: Draft Final Report Nov. 1, 17:00; 10: Upload Final Presenation Nov. 7, 17:00; 11: Upload Final Report Nov. 15, 17:00